## outputs
ht output |  |  |  |  | hs output |  |  |  |  | assembly output |  |  |  |  | delivery output
Date | Target output | Acutal output | Target output cumulated | Acutal output cumulated | Date | Target output | Acutal output | Target output cumulated | Acutal output cumulated | Date | Target output | Acutal output | Target output cumulated | Acutal output cumulated | Date | Target output | Acutal output | Target output cumulated | Acutal output cumulated
2023-12-01 | 8000 | 8316 | 8000 | 8316 | 2023-12-01 | 8000 | 7865 | 8000 | 7865 | 2023-12-01 | 8200 | 8232 | 8200 | 8232 | 2023-12-01 | 8200 | 8221 | 8200 | 8221
2023-12-02 | 8000 | 7742 | 16000 | 16058 | 2023-12-02 | 8000 | 8121 | 16000 | 15986 | 2023-12-02 | 8200 | 8391 | 16400 | 16623 | 2023-12-02 | 8200 | 8295 | 16400 | 16516
2023-12-03 | 0 | 0 | 16000 | 16058 | 2023-12-03 | 0 | 0 | 16000 | 15986 | 2023-12-03 | 0 | 0 | 16400 | 16623 | 2023-12-03 | 0 | 0 | 16400 | 16516
2023-12-04 | 8000 | 8141 | 24000 | 24199 | 2023-12-04 | 8000 | 7917 | 24000 | 23903 | 2023-12-04 | 8200 | 8164 | 24600 | 24787 | 2023-12-04 | 8200 | 8179 | 24600 | 24695
2023-12-05 | 8000 | 8309 | 32000 | 32508 | 2023-12-05 | 8000 | 8143 | 32000 | 32046 | 2023-12-05 | 8200 | 8138 | 32800 | 32925 | 2023-12-05 | 8200 | 8138 | 32800 | 32833
2023-12-06 | 8000 | 8066 | 40000 | 40574 | 2023-12-06 | 8000 | 7938 | 40000 | 39984 | 2023-12-06 | 8200 | 8027 | 41000 | 40952 | 2023-12-06 | 8200 | 8188 | 41000 | 41021
2023-12-07 | 8000 | 8372 | 48000 | 48946 | 2023-12-07 | 8000 | 8022 | 48000 | 48006 | 2023-12-07 | 8200 | 8224 | 49200 | 49176 | 2023-12-07 | 8200 | 8220 | 49200 | 49241
2023-12-08 | 8000 | 8036 | 56000 | 56982 | 2023-12-08 | 8000 | 7989 | 56000 | 55995 | 2023-12-08 | 8200 | 8120 | 57400 | 57296 | 2023-12-08 | 8200 | 8136 | 57400 | 57377
2023-12-09 | 8000 | 7727 | 64000 | 64709 | 2023-12-09 | 8000 | 8055 | 64000 | 64050 | 2023-12-09 | 8200 | 8081 | 65600 | 65377 | 2023-12-09 | 8200 | 8282 | 65600 | 65659
2023-12-10 | 0 | 0 | 64000 | 64709 | 2023-12-10 | 0 | 0 | 64000 | 64050 | 2023-12-10 | 0 | 0 | 65600 | 65377 | 2023-12-10 | 0 | 0 | 65600 | 65659
2023-12-11 | 8000 | 7527 | 72000 | 72236 | 2023-12-11 | 8000 | 8135 | 72000 | 72185 | 2023-12-11 | 8200 | 8188 | 73800 | 73565 | 2023-12-11 | 8200 | 8215 | 73800 | 73874
2023-12-12 | 8000 | 8103 | 80000 | 80339 | 2023-12-12 | 8000 | 8071 | 80000 | 80256 | 2023-12-12 | 8200 | 8085 | 82000 | 81650 | 2023-12-12 | 8200 | 8138 | 82000 | 82012
2023-12-13 | 8000 | 8101 | 88000 | 88440 | 2023-12-13 | 8000 | 7803 | 88000 | 88059 | 2023-12-13 | 8200 | 8218 | 90200 | 89868 | 2023-12-13 | 8200 | 8283 | 90200 | 90295
2023-12-14 | 8000 | 7740 | 96000 | 96180 | 2023-12-14 | 8000 | 8150 | 96000 | 96209 | 2023-12-14 | 8200 | 8024 | 98400 | 97892 | 2023-12-14 | 8200 | 8243 | 98400 | 98538
2023-12-15 | 8000 | 8285 | 104000 | 104465 | 2023-12-15 | 8000 | 8000 | 104000 | 104209 | 2023-12-15 | 8200 | 8020 | 106600 | 105912 | 2023-12-15 | 8200 | 8219 | 106600 | 106757
2023-12-16 | 8000 | 8073 | 112000 | 112538 | 2023-12-16 | 8000 | 8025 | 112000 | 112234 | 2023-12-16 | 8200 | 8311 | 114800 | 114223 | 2023-12-16 | 8200 | 8153 | 114800 | 114910
2023-12-17 | 0 | 0 | 112000 | 112538 | 2023-12-17 | 0 | 0 | 112000 | 112234 | 2023-12-17 | 0 | 0 | 114800 | 114223 | 2023-12-17 | 0 | 0 | 114800 | 114910
2023-12-18 | 8000 | 7931 | 120000 | 120469 | 2023-12-18 | 8000 | 7953 | 120000 | 120187 | 2023-12-18 | 8200 | 8377 | 123000 | 122600 | 2023-12-18 | 8200 | 8182 | 123000 | 123092
2023-12-19 | 8000 | 8200 | 128000 | 128669 | 2023-12-19 | 8000 | 7939 | 128000 | 128126 | 2023-12-19 | 8200 | 8288 | 131200 | 130888 | 2023-12-19 | 8200 | 8115 | 131200 | 131207
2023-12-20 | 8000 | 7527 | 136000 | 136196 | 2023-12-20 | 8000 | 8012 | 136000 | 136138 | 2023-12-20 | 8200 | 8354 | 139400 | 139242 | 2023-12-20 | 8200 | 8104 | 139400 | 139311
2023-12-21 | 0 | 0 | 136000 | 136196 | 2023-12-21 | 0 | 0 | 136000 | 136138 | 2023-12-21 | 0 | 0 | 139400 | 139242 | 2023-12-21 | 0 | 0 | 139400 | 139311
2023-12-22 | 7500 | 6908 | 143500 | 143104 | 2023-12-22 | 7500 | 7989 | 143500 | 144127 | 2023-12-22 | 8000 | 8053 | 147400 | 147295 | 2023-12-22 | 8000 | 8206 | 147400 | 147517
2023-12-23 | 7500 | 7305 | 151000 | 150409 | 2023-12-23 | 7500 | 7600 | 151000 | 151727 | 2023-12-23 | 8000 | 8140 | 155400 | 155435 | 2023-12-23 | 8000 | 8178 | 155400 | 155695
2023-12-24 | 0 | 0 | 151000 | 150409 | 2023-12-24 | 0 | 0 | 151000 | 151727 | 2023-12-24 | 0 | 0 | 155400 | 155435 | 2023-12-24 | 0 | 0 | 155400 | 155695
2023-12-25 | 0 | 0 | 151000 | 150409 | 2023-12-25 | 0 | 0 | 151000 | 151727 | 2023-12-25 | 0 | 0 | 155400 | 155435 | 2023-12-25 | 0 | 0 | 155400 | 155695
2023-12-26 | 8000 | 8002 | 159000 | 158411 | 2023-12-26 | 8000 | 7832 | 159000 | 159559 | 2023-12-26 | 8200 | 8189 | 163600 | 163624 | 2023-12-26 | 8200 | 8182 | 163600 | 163877
2023-12-27 | 8000 | 8011 | 167000 | 166422 | 2023-12-27 | 8000 | 8126 | 167000 | 167685 | 2023-12-27 | 8200 | 8360 | 171800 | 171984 | 2023-12-27 | 8200 | 8147 | 171800 | 172024
2023-12-28 | 8000 | 8002 | 175000 | 174424 | 2023-12-28 | 8000 | 7926 | 175000 | 175611 | 2023-12-28 | 8200 | 8042 | 180000 | 180026 | 2023-12-28 | 8200 | 8265 | 180000 | 180289
2023-12-29 | 8000 | 8014 | 183000 | 182438 | 2023-12-29 | 8000 | 8005 | 183000 | 183616 | 2023-12-29 | 8200 | 8284 | 188200 | 188310 | 2023-12-29 | 8200 | 8295 | 188200 | 188584
2023-12-30 | 8000 | 7890 | 191000 | 190328 | 2023-12-30 | 8000 | 8004 | 191000 | 191620 | 2023-12-30 | 8200 | 8293 | 196400 | 196603 | 2023-12-30 | 8200 | 8250 | 196400 | 196834
2023-12-31 | 0 | 0 | 191000 | 190328 | 2023-12-31 | 0 | 0 | 191000 | 191620 | 2023-12-31 | 0 | 0 | 196400 | 196603 | 2023-12-31 | 0 | 0 | 196400 | 196834

## OPL
S.NO. | DATE | OPEN POINT | DEPARTMENT | REASON | SOLUTION | DUE DATE | STATUS
1 | 2023-12-02 | less output | HT | absenteeism | - | 2023-12-02 | done
2 | 2023-12-05 | machine ALpha breakdown | HS | sensor malfunction | part planned on beta machine | 2023-12-06 | done
3 | 2023-12-10 | customer crtical part no. 11223345 | delivery | machine beta in upgradation | part planned on gamma machine | 2023-12-12 | done
4 | 2023-12-18 | less output | assembly | absenteeism | - | 2023-12-18 | done
5 | 2023-12-22 | less output | HS | absenteeism | - | 2023-12-22 | done
6 | 2023-12-27 | machine upgradation | HS | machine maintance required | - | 2023-12-29 | done
7 | 2023-12-28 | less output | delivery | machine omega breakdown | part planned on gamma machine | 2023-12-28 | pending

## customer Crit.
Date | Part no. | customer name | due date | qty | status
2023-12-10 | 11223345 | yeti corps | 2023-12-12 | 800 | done

## VBL
S. no. | date (week) | part no. | vendor name | due date(week) | qty | status
1 | 1 | 12312345 | big b corps | 2 | 400 | done
2 | 1 | 46565634 | big b corps | 2 | 800 | done
3 | 2 | 76754654 | yeti corps | 3 | 200 | done
4 | 2 | 75688678 | banana ltd | 3 | 100 | done
5 | 3 | 54645645 | yeti corps | 4 | 200 | pending
6 | 3 | 43546547 | banana ltd | 4 | 800 | pending

## Assembly Losses
Resp. | Reasons | 01-Dec-23 | 02-Dec-23 | 03-Dec-23 | 04-Dec-23 | 05-Dec-23 | 06-Dec-23 | 07-Dec-23 | 08-Dec-23 | 09-Dec-23 | 10-Dec-23 | 11-Dec-23 | 12-Dec-23 | 13-Dec-23 | 14-Dec-23 | 15-Dec-23 | 16-Dec-23 | 17-Dec-23 | 18-Dec-23 | 19-Dec-23 | 20-Dec-23 | 21-Dec-23 | 22-Dec-23 | 23-Dec-23 | 24-Dec-23 | 25-Dec-23 | 26-Dec-23 | 27-Dec-23 | 28-Dec-23 | 29-Dec-23 | 30-Dec-23 | 31-Dec-23
TEF | Breakdown Assembly | 70 | 200 | 0 | 300 | 175 | 0 | 300 | 100 | 1100 | 0 | 800 | 850 | 0 | 0 | 450 | 0 | 0 | 0 | 300 | 0 | 0 | 200 | 350 | 0 | 0 | 0 | 300 | 0 | 300 | 0 | 0
TEF | Breakdown Upstream | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LOP | Pre Parts NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MFH-M1 | In house Parts NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MFH | Absentism | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 300 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 0
MFH-M1 | Quality Issue | 150 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0
MFH-M2 | Quality Issue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PQA | Quality Issue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Organisation | Performance Loss | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MFH-E | Fixture Issue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Heatmap
Date | HT | HS | ASSEMBLY | DELIVERY
2023-12-01 | 1 | 0 | 1 | 1
2023-12-02 | 0 | 1 | 1 | 1
2023-12-03 | 1 | 1 | 1 | 1
2023-12-04 | 1 | 0 | 0 | 0
2023-12-05 | 1 | 1 | 0 | 0
2023-12-06 | 1 | 0 | 0 | 0
2023-12-07 | 1 | 1 | 1 | 1
2023-12-08 | 1 | 0 | 0 | 0
2023-12-09 | 0 | 1 | 0 | 1
2023-12-10 | 1 | 1 | 1 | 1
2023-12-11 | 0 | 1 | 0 | 1
2023-12-12 | 1 | 1 | 0 | 0
2023-12-13 | 1 | 0 | 1 | 1
2023-12-14 | 0 | 1 | 0 | 1
2023-12-15 | 1 | 1 | 0 | 1
2023-12-16 | 1 | 1 | 1 | 0
2023-12-17 | 1 | 1 | 1 | 1
2023-12-18 | 0 | 0 | 1 | 0
2023-12-19 | 1 | 0 | 1 | 0
2023-12-20 | 0 | 1 | 1 | 0
2023-12-21 | 1 | 1 | 1 | 1
2023-12-22 | 0 | 1 | 1 | 1
2023-12-23 | 0 | 1 | 1 | 1
2023-12-24 | 1 | 1 | 1 | 1
2023-12-25 | 1 | 1 | 1 | 1
2023-12-26 | 1 | 0 | 0 | 0
2023-12-27 | 1 | 1 | 1 | 0
2023-12-28 | 1 | 0 | 0 | 1
2023-12-29 | 1 | 1 | 1 | 1
2023-12-30 | 0 | 1 | 1 | 1
2023-12-31 | 1 | 1 | 1 | 1